## Project Charter
FINANCE REPORTING MIGRATION ¦ PROJECT CHARTER
Project type | Simulated retail finance reporting migration
Purpose | Replace manually maintained reports with a controlled reporting workflow
Duration | 12 weeks ¦ 12 Oct 2026 – 1 Jan 2027
Your role | Project Data Analyst supporting Project Manager
Workstreams | Requirements; Data & Reporting; UAT; Deployment
Success criteria | Approved requirements; reconciled reporting; UAT sign-off; documented handover
Assumptions | Entirely simulated; fictional team, dates, issues and outcomes
Scope | Reporting specifications, data validation, test coordination, milestone tracking
Out of scope | Live NEXT systems, actual finance data, automated production changes
Tool focus | Google Sheets, Asana, project controls, UAT
NEXT role reference | https://careers.next.co.uk/jobs/77573
Next build step | Import workbook into Google Sheets; add QUERY, XLOOKUP, pivots and conditional formatting

## Milestones
ID | Milestone | Workstream | Due Date | Owner | Status | Acceptance Evidence | Total Tasks | Completed Tasks | Completion % | Milestone Health | Reporting Date
M01 | Requirements signed off | Requirements & Planning | 2026-10-23 | Project Manager | Not Started | Business requirements approved | 4 | 1 | 25% | On Track | 2026-10-09
M02 | Source-to-target mapping approved | Data & Reporting | 2026-11-06 | Data Lead | Not Started | Mappings reviewed | 2 | 0 | 0% | On Track
M03 | First reconciled report | Data & Reporting | 2026-11-20 | Reporting Analyst | Not Started | Totals matched | 3 | 0 | 0% | Critical Risk
M04 | UAT execution complete | User Acceptance Testing | 2026-12-11 | UAT Lead | Not Started | All priority tests resolved | 5 | 0 | 0% | On Track
M05 | Go-live approval | Deployment & Handover | 2026-12-18 | Project Manager | Not Started | Go/no-go decision | 2 | 0 | 0% | Critical Risk
M06 | Handover completed | Deployment & Handover | 2027-01-01 | Operations Lead | Not Started | SOPs and owners agreed | 2 | 0 | 0% | On Track

## Task Register
Task ID | Task | Workstream | Milestone | Start | Due | Owner | Status | Priority | Dependency | Data Type | Days to Due | Delivery Alert | Dependency Status
T001 | Confirm finance report inventory | Requirements & Planning | M01 | 2026-10-12 | 2026-10-16 | Business Analyst | Done | High |  | Simulated | 7 | Completed | No Dependency
T002 | Interview finance stakeholders | Requirements & Planning | M01 | 2026-10-14 | 2026-10-20 | Business Analyst | In Progress | High |  | Simulated | 11 | On Track | No Dependency
T003 | Document KPI definitions | Requirements & Planning | M01 | 2026-10-16 | 2026-10-22 | Reporting Analyst | In Progress | High | T002 | Simulated | 13 | On Track | Blocked
T004 | Approve scope and acceptance criteria | Requirements & Planning | M01 | 2026-10-21 | 2026-10-23 | Project Manager | Not Started | Critical | T003 | Simulated | 14 | On Track | Blocked
T005 | Profile legacy report extracts | Data & Reporting | M02 | 2026-10-20 | 2026-10-27 | Data Lead | In Progress | High | T001 | Simulated | 18 | On Track | Ready
T006 | Prepare source-to-target mapping | Data & Reporting | M02 | 2026-10-24 | 2026-11-01 | Data Lead | Not Started | Critical | T005 | Simulated | 23 | On Track | Blocked
T007 | Define reconciliation controls | Data & Reporting | M03 | 2026-10-27 | 2026-11-05 | Reporting Analyst | Not Started | High | T006 | Simulated | 27 | On Track | Blocked
T008 | Build reporting prototype | Data & Reporting | M03 | 2026-11-03 | 2026-11-14 | Reporting Analyst | Not Started | High | T006 | Simulated | 36 | On Track | Blocked
T009 | Reconcile balances and totals | Data & Reporting | M03 | 2026-11-10 | 2026-11-20 | Data Lead | Not Started | Critical | T008 | Simulated | 42 | On Track | Blocked
T010 | Write UAT scenarios | User Acceptance Testing | M04 | 2026-11-10 | 2026-11-21 | UAT Lead | Not Started | High | T004 | Simulated | 43 | On Track | Blocked
T011 | Prepare UAT test data | User Acceptance Testing | M04 | 2026-11-16 | 2026-11-24 | UAT Lead | Not Started | High | T009 | Simulated | 46 | On Track | Blocked
T012 | Run UAT cycle 1 | User Acceptance Testing | M04 | 2026-11-23 | 2026-12-02 | Finance Tester | Not Started | Critical | T010 | Simulated | 54 | On Track | Blocked
T013 | Triage and assign defects | User Acceptance Testing | M04 | 2026-11-29 | 2026-12-07 | UAT Lead | Not Started | High | T012 | Simulated | 59 | On Track | Blocked
T014 | Retest resolved defects | User Acceptance Testing | M04 | 2026-12-05 | 2026-12-11 | Finance Tester | Not Started | Critical | T013 | Simulated | 63 | On Track | Blocked
T015 | Prepare go-live checklist | Deployment & Handover | M05 | 2026-12-05 | 2026-12-13 | Operations Lead | Not Started | High | T012 | Simulated | 65 | On Track | Blocked
T016 | Obtain business sign-off | Deployment & Handover | M05 | 2026-12-12 | 2026-12-18 | Project Manager | Not Started | Critical | T014 | Simulated | 70 | On Track | Blocked
T017 | Document SOP and ownership | Deployment & Handover | M06 | 2026-12-15 | 2026-12-24 | Operations Lead | Not Started | High | T016 | Simulated | 76 | On Track | Blocked
T018 | Deliver training and handover | Deployment & Handover | M06 | 2026-12-25 | 2027-01-01 | Operations Lead | Not Started | High | T017 | Simulated | 84 | On Track | Blocked
Formulas:
Days to Due = [Due]-TODAY()
Delivery Alert = IF([Status]="Done","Completed",IF([Due]<TODAY(),"Overdue",IF([Due]<=TODAY()+7,"Due Soon","On Track")))

## Task Lookup
Task ID | Task Name
T002 | Interview finance stakeholders
T013 | Triage and assign defects

## Risk and Issue Log
ID | Description | Type | Severity | Owner | Mitigation / Next Action | Status | Milestone
R01 | Delayed requirements sign-off | Risk | High | Project Manager | Agree decision deadline | Open | M01
R02 | Inconsistent legacy finance definitions | Risk | High | Data Lead | Define common KPI dictionary | Open | M02
R03 | Unreconciled opening balances | Issue | Critical | Data Lead | Investigate source and mapping | Open | M03
R04 | Limited UAT tester availability | Risk | Medium | UAT Lead | Book test windows early | Open | M04
R05 | Unresolved critical defects at go-live | Risk | Critical | Project Manager | Enforce sign-off criteria | Open | M05

## UAT Cases
Test ID | Scenario | Expected Result | Status | Tester | Priority | Milestone | Actual Result / Evidence
U001 | Finance totals agree with approved source | Approved source totals match report totals | Pass | Finance Tester | High | M03
U002 | Date filter includes correct period | Only selected accounting period returned | Fail | Finance Tester | Medium | M04 | Simulated: Date filter returned a transaction from the previous accounting period. Linked defect D002.
U003 | User can export approved report | Export matches visible report | Not Run | Finance Tester | Low | M04
U004 | Negative values display correctly | Credits and reversals retain sign | Not Run | Finance Tester | High | M04
U005 | Missing account code flagged | Exception message displayed | Not Run | Finance Tester | High | M04

## Defect Register
Defect ID | Summary | Priority | Status | Owner | UAT Test | Target Date | Notes
D001 | Missing account mapping produces blank value | High | Open | Data Lead | U005 | 2026-11-30 | Simulated issue for testing
D002 | Date filter includes prior-period transaction | Medium | Open | Reporting Analyst | U002 | 2026-12-02 | Simulated issue for testing

## Overview
PROJECT DELIVERY CONTROL CENTRE
KPI | Value
Total tasks | 18
Tasks complete | 1
Tasks blocked | 0
Tasks in progress | 3
Open risks/issues | 5
UAT cases not run | 3
Workstream | Tasks | Completed | Completion %
Requirements & Planning | 4 | 1 | 25%
Data & Reporting | 5 | 0 | 0%
User Acceptance Testing | 5 | 0 | 0%
Deployment & Handover | 4 | 0 | 0%
Important | This is a simulated training portfolio, not real NEXT data
Google Sheets | After import, implement QUERY / XLOOKUP / pivot tables and test results

## Delivery Analysis
Task Status | Number of Tasks
Done | 1
In Progress | 3
Not Started | 14

## Delivery Dashboard
Project Delivery Dashboard
Total Tasks | 18
Completed | 1
In Progress | 3
Not Started | 14
Overdue | 0
Due Soon | 0
Completion Rate | 5.556%
Critical Tasks | 6
High Priority Tasks | 11
Open Risks & Issues | 5
Open Critical Risks & Issues | 2
Severity | Open Items
Critical | 2
High | 2
Medium | 1
Project Management Summary
Project completion is currently 5.56%, with 1 of 18 tasks completed.
Five risks and issues remain open, including two critical items.
Priority attention is required for opening-balance reconciliation and critical defect resolution before go-live.
Recommended next steps are to confirm owners, investigate outstanding issues and monitor milestone dependencies.
UAT Testing Summary |  | Defect Management |  | Release Readiness
Total Test Cases | 5 | Total Defects | 2 | Go-Live Decision | NOT READY
Passed | 1 | Open Defects | 2
Failed | 1 | Open High-Priority Defects | 1
Not Run | 3
Pass Rate | 50%
Release Blockers |  | Dependency Summary
UAT Tests Not Run | 3 | Blocked Tasks | 15 | Blocked Critical Tasks | 6
Failed UAT Tests | 1 | Ready Tasks | 1
Open Defects | 2 | Tasks without Dependencies | 2
Open Critical Risks & Issues | 2
Release blocked: 3 UAT tests not run; 1 failed UAT test; 2 open defects; 2 open critical risks/issues

## Priority Action List
Task ID | Task | Owner | Priority | Due Date | Waiting On | Dependency Status
T004 | Approve scope and acceptance criteria | Project Manager | Critical | 2026-10-23 | T003 | Blocked
T006 | Prepare source-to-target mapping | Data Lead | Critical | 2026-11-01 | T005 | Blocked
T009 | Reconcile balances and totals | Data Lead | Critical | 2026-11-20 | T008 | Blocked
T012 | Run UAT cycle 1 | Finance Tester | Critical | 2026-12-02 | T010 | Blocked
T014 | Retest resolved defects | Finance Tester | Critical | 2026-12-11 | T013 | Blocked
T016 | Obtain business sign-off | Project Manager | Critical | 2026-12-18 | T014 | Blocked